## Sheet1
Phase | Department | Room No. | Room Name | Resp | Type | Status | PO Status | Photo | Lease qty | DNP qty | Net New | Unit Budget | Total Budget | PO qty | PO amt | PO delta | PO Number | Delivered Date | CAD ID | Room Count | Planned qty | Shop Drawing | Flag | Lead Time | Install Date | Profile | Cost Center
Phase 1 | Emergency |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency |  | Office | EXCI | EXISTING | Plan | None | TRUE | 0 | 0 | 0 | 5472 | 0 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 1 | Emergency |  | Office | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency |  | Office | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 138.52 | 138.52 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 100 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 100 | Exam | EXCI | EXISTING | Plan | None | TRUE | 0 | 0 | 0 | 5472 | 0 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | 492024
Phase 1 | Emergency | 100 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 100 | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 100 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 100 | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 101 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 101 | Exam | EXCI | EXISTING | Plan | None | TRUE | 0 | 0 | 0 | 5472 | 0 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | 492024
Phase 1 | Emergency | 101 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 101 | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 101 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 101 | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 102 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 102 | Exam | EXCI | EXISTING | Plan | None | TRUE | 0 | 0 | 0 | 5472 | 0 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | 492024
Phase 1 | Emergency | 102 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 102 | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 102 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 102 | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 1 | Emergency | 102 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 138.52 | 138.52 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 2 | Emergnecy | 200 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 2 | Emergnecy | 200 | Exam | EXCI | EXISTING | Plan | None | TRUE | 0 | 0 | 0 | 5472 | 0 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | 492024
Phase 2 | Emergnecy | 200 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 2 | Emergnecy | 200 | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 2 | Emergnecy | 200 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 2 | Emergnecy | 200 | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | 394853
Phase 2 | Emergnecy | 201 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy | 201 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy | 201 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy | 201 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy | 201 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy | 201 | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy | 202 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy | 202 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy | 202 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy | 202 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy | 202 | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy | 202 | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 40 | 60 | 2400 | 0 | 0 | 0 |  |  |  | 40 | 40 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 40 | 5472 | 218880 | 0 | 0 | 0 |  |  |  | 40 | 40 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 40 | 274.34 | 10973.6 | 0 | 0 | 0 |  |  |  | 40 | 40 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 40 | 112.5 | 4500 | 0 | 0 | 0 |  |  |  | 40 | 40 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 40 | 539.93 | 21597.2 | 0 | 0 | 0 |  |  |  | 40 | 40 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 40 | 31.37 | 1254.8 | 0 | 0 | 0 |  |  |  | 40 | 40 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam (BH) | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 60 | 60 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam (BH) | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 5472 | 5472 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  | Options Pending | CAP
Phase 2 | Emergnecy |  | Exam (BH) | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 274.34 | 274.34 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam (BH) | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 112.5 | 112.5 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam (BH) | OFOI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 539.93 | 539.93 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP
Phase 2 | Emergnecy |  | Exam (BH) | OFCI | NEW | Plan | None | TRUE | 0 | 0 | 1 | 31.37 | 31.37 | 0 | 0 | 0 |  |  |  | 1 | 1 | FALSE |  |  |  |  | CAP